## Sheet1
Week 9
Hour 1 | Created new project without DAL and 3-tier architecture
Hour 2 | Worked on minor Contact Us page css changes
Hour 3 | Sat with Pasindu for appointment index page returning list of appointments
Hour 4 | Sat with Pasindu for appointment index page returning list of appointments
Hour 5 | Sat with Pasindu for appointment index page returning list of appointments
Hour 6 | Created Booking appointment Index page with table
Hour 7 | Integrated works done by Saugat and Angi and pushed into github
Hour 8 | Worked on redirecting non-logged in user to login page when click on Appointment tab
Hour 9 | Worked on redirecting non-logged in user to login page when click on Appointment tab
Hour 10 | Ran issues returning UserID into Create appointment page
Hour 11 | Researched about the issue returning UserID
Hour 12 | Sat with Chrishan for returning UserID as it was saved null in db
Hour 13 | Sat with Chrishan for returning UserID as it was saved null in db
Hour 14 | Sat with Chrishan for returning UserID as it was saved null in db
Hour 15 | Sat with Chrishan for returning UserID as it was saved null in db
Hour 16 | Sat with Chrishan for returning UserID as it was saved null in db
Hour 17 | Returned user email as UserID and auto-populated it while logged in user creates Appointment
Hour 18 | Worked on displaying time ranges on Time field after selecting a date
Hour 19 | Worked on displaying time ranges on Time field after selecting a date
Hour 20 | Worked on displaying time ranges on Time field after selecting a date
Hour 21 | Group meetings regarding project progress and individual issues
Hour 22 | Setup Trello cards about Week 9 and for next week 10